## Sheet5
Subcomponents | Sum of CRI (MZN) | Sum of Government (MZN) | Sum of Beneficiaries (MZN) | Sum of Cost
Subcomponent 1 - Access to affordable and basic assets | 1082033.4702 | 13088.096 | 48547.5213 | 1143669.0875
Subcomponent 2 - Small Scale Infrastructure and Equipment | 518629.6179 | 0 | 57625.5131 | 576255.131
Subcomponent 3 - Access to short-term finance | 450742.0272 | 0 | 0 | 450742.0272
Subcomponent 4 - Project Management and Oversight | 126302.4945 | 0 | 0 | 126302.4945
Grand Total | 2177707.6097 | 13088.096 | 106173.0344 | 2296968.7401
No de gaiolas implantadas
Nr de unidade expandida/concluida
No de tanques implantados/reabilitados
No de alevinos adquiridos
Kilogramas de ração adquirida
No de maquinetas adquiridas
No de sessoes realizadas
No de sessoes realizadas
No de sessoes realizadas
No de sessoes realizadas
No de jovens treinados
No de kits adquiridos
No de missoes realizadas
No de missoes realizadas
No de kits adquiridos
No de grupos organizados
# of FO and MSMEs supported
# of FO and MSMEs supported
Nr de individuos financiados | # of entities financed | Active borrowers (individuals)
Nr de individuos financiados | # of entities financed
Nr de individuos financiados | # of entities financed
Nr de unidades de racao financiadas | # of entities financed
Nr de unidades de alevenios fianciados | # of entities financed
Nr de gaiolas financiados | # of entities financed
Nr de tanques financiados | # of entities financed
No de dispositivos electronicos adquiridos
No de sistemas instalados
No de divulgações na rádio
No de feiras realizadas

## MIMAIP
Componentes | Acções | Meta |  | Indicador | Estimativa de beneficiários directos |  |  | Informações adicionais | Tipo de despesa | Custo Unitário (MT) | Custo Total (MT) | Custo Total (US$)
[5 empty] | Total | Homens | Mulheres
Component 1 | Implantação de unidades de gaiolas flutuantes | 25 | Fishponds constructed/rehabilitated | No de gaiolas implantadas | 25 | 10 | 15 | 25 gaiolas flutuantes em Niassa produção esperada de 43 toneladas por ciclo | Servicos | 200000 | 5000000 | 78125 |  | 3156.5657 | 78914.1414
| Expansao/Conclusao de Unidade de Producao de Racao em Lichinga | 1 | Processing facilities constructed/rehabilitated | Nr de unidade expandida/concluida | 1 | 1 | 0 |  |  | 3200000 | 3200000 | 50000 |  | 50505.0505 | 50505.0505
| Reabilitacao e Expansao tanques aquicolas resilientes as mudanças climáticas em Milange e Ribuae | 80 | Fishponds constructed/rehabilitated | No de tanques implantados/reabilitados | 80 | 40 | 40 | 80 tanques - produção esperada de 84 toneladas por ciclo | Servicos & Bens | 115200 | 9216000 | 144000 |  | 1818.1818 | 145454.5455
| Fornecimento de insumos aquicolas - Alevinos | 450000 | # of households assessing inputs and/or technological packages | No de alevinos adquiridos | 90 | 30 | 60 | 450.000 alevinos (300.000 para gaiolas e 90.000 para tanques) | Bens | 8 | 3600000 | 56250 |  | 0.12626 | 56818.1818
| Fornecimento de insumos aquicolas - Ração | 192000 | # of households assessing inputs and/or technological packages | Kilogramas de ração adquirida | 90 | 30 | 60 | 192.000 kg de racao | Bens | 96 | 18432000 | 288000 |  | 1.5152 | 290909.0909
| Aquisicao de maquinetas de producao de racao para Zambezia e Nampula | 8 | Processing facilities constructed/rehabilitated | No de maquinetas adquiridas | 90 | 30 | 60 | Maquinetas para moer, misturar ingreidentes e peletizar | Bens | 35200 | 281600 | 4400 |  | 555.5556 | 4444.4444
| Treinamento de extensionistas em técnicas de cultivo de peixe em tanques e gaiolas em Niassa, Zambezia e Nampula | 6 | # of public and private entities staff trained | No de sessoes realizadas | 30 | 15 | 15 |  | Custos Operacionais | 494080 | 2964480 | 46320 |  | 7797.9798 | 46787.8788
| Treinamento de aquacultores em técnicas de cultivo de peixe em tanques e gaiolasm Niassa, Zambezia e Nampula | 6 | # of people trained in fish production and technologies | No de sessoes realizadas | 90 | 30 | 60 | Treinamento dos aquacultores em matérias de (i) abertura de tanques (ii) construção de gaiolas (iii) gestão do cultivo (iv) produção de dietas melhoradas (v) técnicas de colheita (VI) boas praticas (VII) dissiminacao de tecnicas melhoradas | Custos Operacionais | 96000 | 576000 | 9000 |  | 1515.1515 | 9090.9091
| Treinamento de intervenientes na cadeia de valor de aquacultura em tecnologia de pescado | 3 | # of people trained in fish production and technologies | No de sessoes realizadas | 90 | 30 | 60 | Capacitação em boas práticas de manuseamento, conservação, tecnologias melhoradas de processamento e agregacao de valor ao pescado | Custos operacionais | 324637 | 973911 | 15217.3594 |  | 5123.69 | 15371.0701
| Treinamento de intervenientes em gestão de negócios e acesso a mercados na cadeia de valor de aquacultura | 3 | # of people trained in business and entrepreneurship | No de sessoes realizadas | 90 | 30 | 60 | Capacitação de aquacultores e comerciantes em materias de gestao de negocios, acesso aos mercados e iniciativas de geracao de rendimentos na cadeia de valor da aquacultura | Custos operacionais | 324637 | 973911 | 15217.3594 |  | 5123.69 | 15371.0701
| Treinamento vocacional de jovens para o empreendedorismo nas actividades de apoio a cadeia de valor de aquacultura (refrigeracao, electricidade, sistema solar, serralharia, construcao civil, carpintaria, mecanica) | 15 | People (youth) receiving vocational training | No de jovens treinados | 15 | 7 | 8 | treinamento em refrigeracao, electricidade, mecanica, serralharia, carpintaria | Custos operacionais | 128000 | 1920000 | 30000 |  | 2020.202 | 30303.0303
| Aquisicao e fornecimento de kits de empreendedorismo para os jovens | 15 | People receiving enterpreneurship kits | No de kits adquiridos | 15 | 7 | 8 | Kits de material de refrigeracao, electricidade, mecanica, serralharia, carpintaria | Bens & Servicos | 147200 | 2208000 | 34500 |  | 2323.2323 | 34848.4848
| Assistência técnica aos aquacultores | 48 |  | No de missoes realizadas | 90 | 30 | 60 | Os aquacultores serão assistidos em maneio geral do cultivo e boas praticas | Custos Operacionais | 6400 | 307200 | 4800 |  | 101.0101 | 4848.4848
| Missoes de monitoria das actividades de promocao da aquacultores e de grupos de aquacultores | 10 |  | No de missoes realizadas |  |  |  |  | Custos Operacionais | 324637 | 3246370 | 50724.5312 |  | 5123.69 | 51236.9003
| Aquicisao de kits de manuseamento e conseravacao do pescado [caixas isotermicas, balanca, facas e tabuas de evisceracao] | 90 | Processing facilities constructed/rehabilitated | No de kits adquiridos | 90 | 30 | 60 |  |  | 34000 | 3060000 | 47812.5 |  | 536.6162 | 48295.4545
| Organização de piscicultores em grupos | 3 | Production groups formed/ strengthened | No de grupos organizados | 90 | 30 | 60 |  | Custos Operacionais & Servicos | 324637 | 973911 | 15217.3594 |  | 5123.69 | 15371.0701
Componente 2 - Acesso a informação do mercado | Aquisição dispositivos elecrtonicos para operacionalização do sistema de recolha de preços | 46 | # of electronic data collection and retrieval devices allocated | No de dispositivos electronicos adquiridos | 90 | 30 | 60 | Recolha de informação estatística de base nos locais de produção, de venda de pescado | Custos operacionais | 10000 | 460000 | 7187.5 |  | 157.8283 | 7260.101
| Instalação do sistema de recolha de informação de sobre mercados de pesca e aquacultura | 7 | # of management information systems operational | No de sistemas instalados | 90 | 30 | 60 | Instalados sistemas de recolha de dados nas Delegações provinciais do IDEPA | Custos operacionais | 715000 | 5005000 | 78203.125 |  | 11284.7222 | 78993.0556
| Recolha e divulgação de preços de insumos e pescado | 276 |  | No de divulgações na rádio | 90 | 30 | 60 | As informações serão divulgadas em todos os distritos do PRODAPE, sendo uma por mês | Custos operacionais | 7000 | 1932000 | 30187.5 |  | 110.4798 | 30492.4242
| Realizacao de feiras locais de pescado em Niassa, Nampula e Zambezia | 3 |  | No de feiras realizadas | 500 | 200 | 300 | Promocao de produtos, insumos e servicos da aquacultura | Custos operacionais | 128000 | 384000 | 6000 |  | 2020.202 | 6060.6061
Componente 3 - Acesso ao financiamento | Financiar a aquisicao de equipamento de frio, material de manuseamento e conservacao de pescado [ fabriqueta de gelo, congeladores, caixas isotermicas ] | 25 | Processing facilities constructed/rehabilitated | Nr de individuos financiados | 25 | 10 | 15 | Fabriqueta de producao de gelo, camara de conservacao de pescado, arcas frigorificas, caixas isotérmicas | Servicos | 70000 | 1750000 | 27343.75 |  | 1104.798 | 27619.9495
| Financiar a aquisicao de insumos de producao | 60 | # of households assessing inputs and/or technological packages | Nr de individuos financiados | 60 | 30 | 30 | Gaiolas, tanques, ração, alevinos, maquinetas de racao e outros equipamentos | Servicos | 115200 | 6912000 | 108000 |  | 1818.1818 | 109090.9091
| Financiamento a iniciativa de negócios na cadeia de valor da aquacultura. | 15 | # of households assessing inputs and/or technological packages | Nr de individuos financiados | 15 | 8 | 7 | Projecto de negocios, incluindo iniciativas de empereendedorismo para jovens | Servicos | 200000 | 3000000 | 46875 |  | 3156.5657 | 47348.4848
| Finnciamento de expansao de unidades de producao de racao de nivel comercial | 1 | # of households assessing inputs and/or technological packages | Nr de unidades de racao financiadas | 1 | 1 | 0 |  |  | 4800000 | 4800000 | 75000 |  | 75757.5758 | 75757.5758
| Financiamento de expansao unidades de producao de alevinos | 3 | # of households assessing inputs and/or technological packages | Nr de unidades de alevenios fianciados | 3 | 2 | 1 |  |  | 2560000 | 7680000 | 120000 |  | 40404.0404 | 121212.1212
| Financiamento de expansao de unidades de producao de gaiolas | 15 | # of households assessing inputs and/or technological packages | Nr de gaiolas financiados | 15 | 8 | 7 |  |  | 200000 | 3000000 | 46875 |  | 3156.5657 | 47348.4848
| Financiamento de expansao de unidades de producao de tanques | 60 | # of households assessing inputs and/or technological packages | Nr de tanques financiados | 60 | 30 | 30 |  |  | 80000 | 4800000 | 75000 |  | 1262.6263 | 75757.5758
Total [valor do REFP e Custo total para Aquacultura] | [10 empty] | 96656383 | 1510255.9844 |  | 0 | 1525511.0953
[9 empty] | Valor a ser financiado pelo REEFP |  |  | 499093.75 |  | 0 | 0
[5 empty] | 615 |  |  |  | Custo Total do Projecto Para Aquacultura |  |  | 1011162.2344 |  | 0 | 0
| Activity | Indicator |  | Units | Freq. | Quantity | Unit Price (MZN) | Cost | Priority | Geographical Distribution, ex. Mapai (22), Mabalane (16) | Comments | Component
| Implantação de unidades de gaiolas flutuantes | No de gaiolas implantadas |  |  | 1 | 25 | 3156.5657 | 78914.1414 | High |  |  | Subcomponent 1 - Access to affordable and basic assets | Servicos
| Expansao/Conclusao de Unidade de Producao de Racao em Lichinga | Nr de unidade expandida/concluida |  |  | 1 | 1 | 50505.0505 | 50505.0505 | High |  |  | Subcomponent 1 - Access to affordable and basic assets
| Reabilitacao e Expansao tanques aquicolas resilientes as mudanças climáticas em Milange e Ribuae | No de tanques implantados/reabilitados |  |  | 1 | 80 | 1818.1818 | 145454.5455 | High |  |  | Subcomponent 1 - Access to affordable and basic assets | Servicos & Bens
| Fornecimento de insumos aquicolas - Alevinos | No de alevinos adquiridos |  |  | 1 | 450000 | 0.12626 | 56818.1818 | High |  |  | Subcomponent 1 - Access to affordable and basic assets | Bens
| Fornecimento de insumos aquicolas - Ração | Kilogramas de ração adquirida |  |  | 1 | 192000 | 1.5152 | 290909.0909 | High |  |  | Subcomponent 1 - Access to affordable and basic assets | Bens
| Aquisicao de maquinetas de producao de racao para Zambezia e Nampula | No de maquinetas adquiridas |  |  | 1 | 8 | 555.5556 | 4444.4444 | High |  |  | Subcomponent 1 - Access to affordable and basic assets | Bens
| Treinamento de extensionistas em técnicas de cultivo de peixe em tanques e gaiolas em Niassa, Zambezia e Nampula | No de sessoes realizadas |  |  | 1 | 6 | 7797.9798 | 46787.8788 | High |  |  | Subcomponent 1 - Access to affordable and basic assets | Custos Operacionais
| Treinamento de aquacultores em técnicas de cultivo de peixe em tanques e gaiolasm Niassa, Zambezia e Nampula | No de sessoes realizadas |  |  | 1 | 6 | 1515.1515 | 9090.9091 | High |  |  | Subcomponent 1 - Access to affordable and basic assets | Custos Operacionais
| Treinamento de intervenientes na cadeia de valor de aquacultura em tecnologia de pescado | No de sessoes realizadas |  |  | 1 | 3 | 5123.69 | 15371.0701 | High |  |  | Subcomponent 1 - Access to affordable and basic assets | Custos operacionais
| Treinamento de intervenientes em gestão de negócios e acesso a mercados na cadeia de valor de aquacultura | No de sessoes realizadas |  |  | 1 | 3 | 5123.69 | 15371.0701 | High |  |  | Subcomponent 1 - Access to affordable and basic assets | Custos operacionais
| Treinamento vocacional de jovens para o empreendedorismo nas actividades de apoio a cadeia de valor de aquacultura (refrigeracao, electricidade, sistema solar, serralharia, construcao civil, carpintaria, mecanica) | No de jovens treinados |  |  | 1 | 15 | 2020.202 | 30303.0303 | High |  |  | Subcomponent 1 - Access to affordable and basic assets | Custos operacionais
| Aquisicao e fornecimento de kits de empreendedorismo para os jovens | No de kits adquiridos |  |  | 1 | 15 | 2323.2323 | 34848.4848 | High |  |  | Subcomponent 1 - Access to affordable and basic assets | Bens & Servicos
| Assistência técnica aos aquacultores | No de missoes realizadas |  |  | 1 | 48 | 101.0101 | 4848.4848 | High |  |  | Subcomponent 1 - Access to affordable and basic assets | Custos Operacionais
| Missoes de monitoria das actividades de promocao da aquacultores e de grupos de aquacultores | No de missoes realizadas |  |  | 1 | 10 | 5123.69 | 51236.9003 | High |  |  | Subcomponent 1 - Access to affordable and basic assets | Custos Operacionais
| Aquicisao de kits de manuseamento e conseravacao do pescado [caixas isotermicas, balanca, facas e tabuas de evisceracao] | No de kits adquiridos |  |  | 1 | 90 | 536.6162 | 48295.4545 | High |  |  | Subcomponent 1 - Access to affordable and basic assets
| Organização de piscicultores em grupos | No de grupos organizados |  |  | 1 | 3 | 5123.69 | 15371.0701 | High |  |  | Subcomponent 1 - Access to affordable and basic assets | Custos Operacionais & Servicos
| Aquisição dispositivos elecrtonicos para operacionalização do sistema de recolha de preços | No de dispositivos electronicos adquiridos |  |  | 1 | 46 | 157.8283 | 7260.101 | High |  |  | Componente 2 - Acesso a informação do mercado | Custos operacionais
| Instalação do sistema de recolha de informação de sobre mercados de pesca e aquacultura | No de sistemas instalados |  |  | 1 | 7 | 11284.7222 | 78993.0556 | High |  |  | Componente 2 - Acesso a informação do mercado | Custos operacionais
| Recolha e divulgação de preços de insumos e pescado | No de divulgações na rádio |  |  | 1 | 276 | 110.4798 | 30492.4242 | High |  |  | Componente 2 - Acesso a informação do mercado | Custos operacionais
| Realizacao de feiras locais de pescado em Niassa, Nampula e Zambezia | No de feiras realizadas |  |  | 1 | 3 | 2020.202 | 6060.6061 | High |  |  | Componente 2 - Acesso a informação do mercado | Custos operacionais
| Financiar a aquisicao de equipamento de frio, material de manuseamento e conservacao de pescado [ fabriqueta de gelo, congeladores, caixas isotermicas ] | Nr de individuos financiados |  |  | 1 | 25 | 1104.798 | 27619.9495 | High |  |  | Subcomponent 3 - Access to short-term finance | Servicos
| Financiar a aquisicao de insumos de producao | Nr de individuos financiados |  |  | 1 | 60 | 1818.1818 | 109090.9091 | High |  |  | Subcomponent 3 - Access to short-term finance | Servicos
| Financiamento a iniciativa de negócios na cadeia de valor da aquacultura. | Nr de individuos financiados |  |  | 1 | 15 | 3156.5657 | 47348.4848 | High |  |  | Subcomponent 3 - Access to short-term finance | Servicos
| Finnciamento de expansao de unidades de producao de racao de nivel comercial | Nr de unidades de racao financiadas |  |  | 1 | 1 | 75757.5758 | 75757.5758 | High |  |  | Subcomponent 3 - Access to short-term finance
| Financiamento de expansao unidades de producao de alevinos | Nr de unidades de alevenios fianciados |  |  | 1 | 3 | 40404.0404 | 121212.1212 | High |  |  | Subcomponent 3 - Access to short-term finance
| Financiamento de expansao de unidades de producao de gaiolas | Nr de gaiolas financiados |  |  | 1 | 15 | 3156.5657 | 47348.4848 | High |  |  | Subcomponent 3 - Access to short-term finance
| Financiamento de expansao de unidades de producao de tanques | Nr de tanques financiados |  |  | 1 | 60 | 1262.6263 | 75757.5758 | High |  |  | Subcomponent 3 - Access to short-term finance

## Sheet1
Subcomponents | Sum of CRI Financing (US$) | Sum of GoM (US$) | Sum of Beneficiaries (US$) | TOTAL COST (US$)
Access to affordable inputs and basic assets | 2905874.0085 | 282631.3608 | 147158.2028 | 3335663.5721
Access to short-term finance | 1555099.4632 | 56112.5145 | 27628.6707 | 1638840.6484
Grand Total | 4460973.4717 | 338743.8753 | 174786.8734 | 4974504.2205

## RESUMO LIGADO
Priority | High
Row Labels | REFP (US$) | PROCAVA (US$) | PRODAPE (US$) | GoM (US$) | Beneficiaries (US$) | TOTAL PROJECT COST (US$)
Consultancies, Trainings and Services | 51310.3884 | 0 | 262943.8349 | 34846.1149 | 27205.0245 | 376305.3626
Equipment and Materials | 0 | 1001539.3117 | 165719.6183 | 103851.5793 | 46374.0769 | 1317484.5862
Funds | 951215.6615 | 0 | 552573.4133 | 47560.7831 | 27628.6707 | 1578978.5286
Operating Costs | 0 | 0 | 22734.2394 | 11169.7177 |  | 33903.9571
Grand Total | 1002526.0499 | 1001539.3117 | 1003971.1059 | 197428.1949 | 101207.772 | 3306672.4344
Priority | High
Row Labels | CRI Financing (US$) | GoM (US$) | Beneficiaries (US$) | TOTAL PROJECT COST (US$)
Consultancies, Trainings and Services | 314254.2232 | 34846.1149 | 27205.0245 | 376305.3626
Equipment and Materials | 1167258.93 | 103851.5793 | 46374.0769 | 1317484.5862
Funds | 1503789.0748 | 47560.7831 | 27628.6707 | 1578978.5286
Operating Costs | 22734.2394 | 11169.7177 |  | 33903.9571
Grand Total | 3008036.4675 | 197428.1949 | 101207.772 | 3306672.4344
Priority | High
Row Labels | CRI Financing (US$) | GoM (US$) | Beneficiaries (US$) | Total
Access to affordable inputs and basic assets | 1452937.0043 | 141315.6804 | 73579.1014 | 1667831.7861
Access to short-term finance | 1555099.4632 | 56112.5145 | 27628.6707 | 1638840.6484
Grand Total | 3008036.4675 | 197428.1949 | 101207.772 | 3306672.4344
Priority | High
Row Labels | REFP (US$) | PROCAVA (US$) | PRODAPE (US$) | Beneficiaries (US$) | GoM (US$) | Total
Access to affordable inputs and basic assets | 0 | 1001539.3117 | 451397.6926 | 73579.1014 | 141315.6804 | 1667831.7861
Access to short-term finance | 1002526.0499 | 0 | 552573.4133 | 27628.6707 | 56112.5145 | 1638840.6484
Grand Total | 1002526.0499 | 1001539.3117 | 1003971.1059 | 101207.772 | 197428.1949 | 3306672.4344

## DETALHES
# | Detailed Activity Description |  |  | Units | Freq. | Quantity | Unit Price (MZN) |  | TOTAL PROJECT COST (US$) | CRI Financing (US$) | GoM (US$) | Beneficiaries (US$) | [17 empty] | FY 2022 | [12 empty] | FY 2023
[8 empty] | Cost |  |  |  |  | Priority | Geographical Distribution, ex. Mapai (22), Mabalane (16) | Comments | Component | Category | CRI (%) | Government (%) | Beneficiaries (%) | CRI (MZN) | Government (MZN) | Beneficiaries (MZN) | REFP (%) | PROCAVA (%) | PRODAPE (%) | REFP (US$) | PROCAVA (US$) | PRODAPE (US$) | Jan | Feb | Mar | Apr | May | Jun | Jul | Ago | Sep | Oct | Nov | Dec |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Ago | Sep | Oct | Nov | Dec
[30 empty] | FY 2022 Jan: FY 2022 |  | FY 2023
ID | Activity | comps | Indicator | Units | Freq. | Quantity | Unit Price (MZN) | Cost | TOTAL PROJECT COST (US$) | CRI Financing (US$) | GoM (US$) | Beneficiaries (US$) | Priority | Geographical Distribution, ex. Mapai (22), Mabalane (16) | Comments | Component | Category | CRI (%) | Government (%) | Beneficiaries (%) | CRI (MZN) | Government (MZN) | Beneficiaries (MZN) | REFP (%) | PROCAVA (%) | PRODAPE (%) | REFP (US$) | PROCAVA (US$) | PRODAPE (US$) | Jan | Feb | Mar | Apr | May | Jun | Jul | Ago | Sep | Oct | Nov | Dec | Column1 | Jan | Feb | Mar | Apr | May | Jun | Jul | Ago | Sep | Oct | Nov | Dec
| Outreach |  | # of rural producers receiving project services (recorded and coded) | producers |  |  |  | 0 | 0 | 0 | [7 empty] | 0% | 0% | 0% | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
| Potato producers |  | # of rural producers receiving project services (recorded and coded) | producers |  | 200 | 90000 | 0 | 0 | 0 | [7 empty] | 0% | 0% | 0% | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
| Cassava producers |  | # of rural producers receiving project services (recorded and coded) | producers |  | 3000 | 5000 | 0 | 0 | 0 | [7 empty] | 0% | 0% | 0% | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
| Beans producers |  | # of rural producers receiving project services (recorded and coded) | producers |  | 2500 | 6000 | 0 | 0 | 0 | [7 empty] | 0% | 0% | 0% | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
| SUBCOMPONENT 1 - ACCESS TO AFFORDABLE INPUTS AND BASIC ASSETS | Access to affordable inputs and basic assets | [5 empty] | 0 | 1667831.7861 | 1452937.0043 | 141315.6804 | 73579.1014 |  | 0 | [6 empty] | 1452937.0043 | 141315.6804 | 73579.1014 |  |  |  | 0 | 1001539.3117 | 451397.6926 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A | Produce research level planting materials | Access to affordable inputs and basic assets | [5 empty] | 0 | 0 | 0 | [5 empty] | Subcomponent 1 - Access to affordable inputs and basic assets |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
1 | Establish Cassava stems multiplication plots in collaboration with IIAM (new varieties with high starch content) | Access to affordable inputs and basic assets | # of stems, seedlings, cuttings or plantlets produced | units | 1 | 750000 | 1.5 | 17761.2883 | 22201.6104 | 17761.2883 | 4440.3221 |  | High |  |  | Subcomponent 1 - Access to affordable inputs and basic assets | Equipment and Materials | 0.8 | 0.2 | 0 | 17761.2883 | 4440.3221 | 0 |  | 1 | 0 | 0 | 17761.2883 | 0 | FY 2022 Sep: 500000; FY 2022 Oct: 300000
2 | Produce Foundation Irish potato mini-tubers in collaboration with IIAM | Access to affordable inputs and basic assets | kg of seed produced | kg | 1 | 60000 | 30 | 28418.0613 | 35522.5766 | 28418.0613 | 7104.5153 |  | High |  |  | Subcomponent 1 - Access to affordable inputs and basic assets | Equipment and Materials | 0.8 | 0.2 | 0 | 28418.0613 | 7104.5153 | 0 |  | 1 | 0 | 0 | 28418.0613 | 0 | [19 empty] | 30000 | 30000
3 | Produce Foundation Beans in collaboration with IIAM | Access to affordable inputs and basic assets | kg of seed produced | kg | 1 | 1250 | 150 | 2960.2147 | 3700.2684 | 2960.2147 | 740.0537 |  | High |  |  | Subcomponent 1 - Access to affordable inputs and basic assets | Equipment and Materials | 0.8 | 0.2 | 0 | 2960.2147 | 740.0537 | 0 |  | 1 | 0 | 0 | 2960.2147 | 0 | [16 empty] | 1500
[8 empty] | 0 | 0 | 0 | [5 empty] | Subcomponent 1 - Access to affordable inputs and basic assets |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 | 0 | 0
B | Support seed production with emergent farmers and local enterpreneurs | Access to affordable inputs and basic assets | [5 empty] | 0 | 0 | 0 | [5 empty] | Subcomponent 1 - Access to affordable inputs and basic assets |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 | 0 | 0
1 | Establish Certified (C1) Cassava stems with emergent farmers & local enterpreneurs | Access to affordable inputs and basic assets | # of stems, seedlings, cuttings or plantlets produced | units | 1 | 7000000 | 0.75 | 82886.012 | 91174.6132 | 82886.012 | 8288.6012 |  | High |  |  | Subcomponent 1 - Access to affordable inputs and basic assets | Equipment and Materials | 0.90909 | 0.090909 | 0 | 82886.012 | 8288.6012 | 0 |  | 1 | 0 | 0 | 82886.012 | 0 | [19 empty] | 5000000
2 | Produce Certified (C1) Irish potato mini-tubers with emergent farmers & local enterpreneurs | Access to affordable inputs and basic assets | kg of seed produced | kg | 1 | 160000 | 25 | 63151.2472 | 75781.4967 | 63151.2472 | 12630.2494 |  | High |  |  | Subcomponent 1 - Access to affordable inputs and basic assets | Equipment and Materials | 0.83333 | 0.16667 | 0 | 63151.2472 | 12630.2494 | 0 |  | 1 | 0 | 0 | 63151.2472 | 0 | [20 empty] | 3000000
3 | Produce Certified (C1) Beans with emergent farmers & local enterpreneurs | Access to affordable inputs and basic assets | kg of seed produced | kg | 1 | 37500 | 50 | 29602.1471 | 38482.7913 | 29602.1471 | 5920.4294 | 2960.2147 | High |  |  | Subcomponent 1 - Access to affordable inputs and basic assets | Equipment and Materials | 0.76923 | 0.15385 | 0.076923 | 29602.1471 | 5920.4294 | 2960.2147 |  | 1 | 0 | 0 | 29602.1471 | 0 | [18 empty] | 18750 | 18750
[5 empty] | 1 |  |  | 0 | 0 | 0 | [5 empty] | Subcomponent 1 - Access to affordable inputs and basic assets |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 | 0 | 0
C | Procure and allocate trial input support packages | Access to affordable inputs and basic assets | [5 empty] | 0 | 0 | 0 | [5 empty] | Subcomponent 1 - Access to affordable inputs and basic assets |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 | 0 | 0
1 | Cassava input support packages (stems, agrochemicals) | Access to affordable inputs and basic assets | # of households assessing inputs and/or technological packages | households | 1 | 2000 | 5000 | 157878.1181 | 181559.8358 | 157878.1181 | 15787.8118 | 7893.9059 | High |  |  | Subcomponent 1 - Access to affordable inputs and basic assets | Equipment and Materials | 0.86957 | 0.086957 | 0.043478 | 157878.1181 | 15787.8118 | 7893.9059 |  | 1 | 0 | 0 | 157878.1181 | 0 | [18 empty] | 1000 | 1000
2 | Irish potato input support packages (seeds, agrochemicals) | Access to affordable inputs and basic assets | # of households assessing inputs and/or technological packages | households | 1 | 200 | 40000 | 126302.4945 | 145247.8686 | 126302.4945 | 12630.2494 | 6315.1247 | High |  |  | Subcomponent 1 - Access to affordable inputs and basic assets | Equipment and Materials | 0.86957 | 0.086957 | 0.043478 | 126302.4945 | 12630.2494 | 6315.1247 |  | 1 | 0 | 0 | 126302.4945 | 0 | [15 empty] | 200
3 | Beans input support packages (seeds, agrochemicals) | Access to affordable inputs and basic assets | # of households assessing inputs and/or technological packages | households | 1 | 1500 | 6000 | 142090.3063 | 163403.8522 | 142090.3063 | 14209.0306 | 7104.5153 | High |  |  | Subcomponent 1 - Access to affordable inputs and basic assets | Equipment and Materials | 0.86957 | 0.086957 | 0.043478 | 142090.3063 | 14209.0306 | 7104.5153 |  | 1 | 0 | 0 | 142090.3063 | 0 | [15 empty] | 1500
[8 empty] | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 | 0 | 0 | [14 empty] | 0
D | Promote value addition investments | [6 empty] | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 | 0 | 0 | [14 empty] | 0
1 | Establish trials on inclusion of cassava flour on backing industry | Access to affordable inputs and basic assets | # of reports prepared and approved | reports | 1 | 1 | 2200000 | 34733.186 | 34733.186 | 34733.186 |  |  | High |  |  | Subcomponent 2 - Access to short-term finance | Equipment and Materials | 1 | 0 | 0 | 34733.186 | 0 | 0 |  | 1 | 0 | 0 | 34733.186 | 0 | bar: FY 2022 Dec
2 | Establish and pilot a market information system for value chain stakeholders | Access to affordable inputs and basic assets | # of management information sistems - MIS, established and operational | systems | 1 | 1 | 2500000 | 39469.5295 | 39469.5295 | 39469.5295 |  |  | High |  |  | Subcomponent 2 - Access to short-term finance | Equipment and Materials | 1 | 0 | 0 | 39469.5295 | 0 | 0 |  | 1 | 0 | 0 | 39469.5295 | 0 | [14 empty] | 1
3 | Establish pilots on use of renewable energy for value-addition facilities (solar powered processing kits) | Access to affordable inputs and basic assets | # of units | units | 1 | 5 | 1200000 | 94726.8709 | 104199.5579 | 94726.8709 | 4736.3435 | 4736.3435 | High |  |  | Subcomponent 2 - Access to short-term finance | Equipment and Materials | 0.90909 | 0.045455 | 0.045455 | 94726.8709 | 4736.3435 | 4736.3435 |  | 1 | 0 | 0 | 94726.8709 | 0 | [18 empty] | 5
[8 empty] | 0 | 0 | 0 | [5 empty] | Subcomponent 1 - Access to affordable inputs and basic assets |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 | 0 | 0
E | Small Scale Productive Equipment | Access to affordable inputs and basic assets | [5 empty] | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 | 0 | 0
1 | Promote low-cost & energy saving small-scale irrigation systems (solar powered drip kits) | Access to affordable inputs and basic assets | # of units | units | 1 | 5 | 2300000 | 181559.8358 | 199715.8194 | 181559.8358 | 9077.9918 | 9077.9918 | High |  |  | Subcomponent 1 - Access to affordable inputs and basic assets | Equipment and Materials | 0.90909 | 0.045455 | 0.045455 | 181559.8358 | 9077.9918 | 9077.9918 |  | 1 | 0 | 0 | 181559.8358 | 0 | FY 2022 Dec: 5
[8 empty] | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 | 0 | 0
F | Small scale acquaculture facilities, equipment and inputs | Access to affordable inputs and basic assets | [5 empty] | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 | 0 | 0
1 | Installation of floating fish cages in Nampula | Access to affordable inputs and basic assets | # of floating cages installed | units | 1 | 50 | 180000 | 142090.3063 | 163403.8522 | 142090.3063 | 14209.0306 | 7104.5153 | High |  |  | Subcomponent 1 - Access to affordable inputs and basic assets | Consultancies, Trainings and Services | 0.86957 | 0.086957 | 0.043478 | 142090.3063 | 14209.0306 | 7104.5153 |  |  | 1 | 0 | 0 | 142090.3063 | FY 2022 Nov: 10 |  | 20 | 20 | 25
2 | Finalize feed processing facility in Lichinga | Access to affordable inputs and basic assets | Processing facilities constructed/rehabilitated | facilities | 1 | 1 | 2578062.5 | 40701.9656 | 48842.3587 | 40701.9656 | 4070.1966 | 4070.1966 | High |  |  | Subcomponent 1 - Access to affordable inputs and basic assets | Consultancies, Trainings and Services | 0.83333 | 0.083333 | 0.083333 | 40701.9656 | 4070.1966 | 4070.1966 |  |  | 1 | 0 | 0 | 40701.9656 | FY 2022 Nov: 0 |  | 0 |  | 0 |  | 1
3 | Rehabilitation and expansion of climate resilient fish ponds in Milange and Ribáue | Access to affordable inputs and basic assets | Fishponds constructed/rehabilitated | ponds | 1 | 60 | 84613.3333 | 80151.563 | 104197.0319 | 80151.563 | 8015.1563 | 16030.3126 | High |  |  | Subcomponent 1 - Access to affordable inputs and basic assets | Consultancies, Trainings and Services | 0.76923 | 0.076923 | 0.15385 | 80151.563 | 8015.1563 | 16030.3126 |  |  | 1 | 0 | 0 | 80151.563 | FY 2022 Nov: 15 |  | 0 |  | 15 |  | 60
4 | Supply of acquaculture inputs in Zambézia, Niassa and Nampula | Access to affordable inputs and basic assets | # of households assessing inputs and/or technological packages | households | 1 | 900 | 105.1056 | 149344.9045 | 164279.3949 | 149344.9045 | 7467.2452 | 7467.2452 | High |  |  | Subcomponent 1 - Access to affordable inputs and basic assets | Equipment and Materials | 0.90909 | 0.045455 | 0.045455 | 149344.9045 | 7467.2452 | 7467.2452 |  |  | 1 | 0 | 0 | 149344.9045 | [13 empty] | 300 |  | 300 | 300
6 | Alocate feed processing kits to smallholder fish farmers | Access to affordable inputs and basic assets | Processing facilities constructed/rehabilitated | facilities | 1 | 2 | 22805.9375 | 720.1117 | 792.1229 | 720.1117 | 36.0056 | 36.0056 | High |  |  | Subcomponent 1 - Access to affordable inputs and basic assets | Equipment and Materials | 0.90909 | 0.045455 | 0.045455 | 720.1117 | 36.0056 | 36.0056 |  |  | 1 | 0 | 0 | 720.1117 | [14 empty] | 4
7 | Train extension officers on fish production | Access to affordable inputs and basic assets | # of public and private entities staff trained | staff | 1 | 30 | 400670.575 | 18977.1349 | 24561.9937 | 18977.1349 | 5584.8588 |  | High |  |  | Subcomponent 1 - Access to affordable inputs and basic assets | Operating Costs | 0.77262 | 0.22738 | 0 | 18977.1349 | 5584.8588 | 0 |  |  | 1 | 0 | 0 | 18977.1349 | [15 empty] | 30
8 | Train fish farmers on fish production | Access to affordable inputs and basic assets | # of producers trained on sustainable production practices | producers | 1 | 90 | 79325 | 3757.1045 | 9341.9633 | 3757.1045 | 5584.8588 |  | High |  |  | Subcomponent 1 - Access to affordable inputs and basic assets | Operating Costs | 0.40218 | 0.59782 | 0 | 3757.1045 | 5584.8588 | 0 |  |  | 1 | 0 | 0 | 3757.1045 | [16 empty] | 90
9 | Allocate fish handling and conservation kits (isothermal crates, scales, nives and others) | Access to affordable inputs and basic assets | People receiving enterpreneurship kits | producers | 1 | 50 | 19831.25 | 15654.6021 | 17220.0624 | 15654.6021 | 782.7301 | 782.7301 | High |  |  | Subcomponent 1 - Access to affordable inputs and basic assets | Equipment and Materials | 0.90909 | 0.045455 | 0.045455 | 15654.6021 | 782.7301 | 782.7301 |  |  | 1 | 0 | 0 | 15654.6021 | [18 empty] | 50
[8 empty] | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 | 0 | 0
| SUBCOMPONENT 2 - ACCESS TO SHORT-TERM FINANCE | [7 empty] | 1638840.6484 | 1555099.4632 | 56112.5145 | 27628.6707 | [8 empty] | 1555099.4632 | 56112.5145 | 27628.6707 | 3 | 0 | 1 | 1002526.0499 | 0 | 552573.4133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0
A | Establish a line of credit for operating costs (inputs for outgrower schemes and FO) | Access to short-term finance | # of FO and MSMEs supported | entities | 1 | 100 | 490000 | 773602.7787 | 812282.9176 | 773602.7787 | 38680.1389 |  | High |  |  | Subcomponent 2 - Access to short-term finance | Funds | 0.95238 | 0.047619 | 0 | 773602.7787 | 38680.1389 | 0 | 1 |  | 0 | 773602.7787 | 0 | 0 | FY 2022 Nov: 10 |  | 20 | 20 | 25 |  | 25
B | Establish a line of credit for small-scale investments (farm mechanization, value-addition, transportation & marketing) | Access to short-term finance | # of FO and MSMEs supported | entities | 1 | 45 | 250000 | 177612.8829 | 186493.527 | 177612.8829 | 8880.6441 |  | High |  |  | Subcomponent 2 - Access to short-term finance | Funds | 0.95238 | 0.047619 | 0 | 177612.8829 | 8880.6441 | 0 | 1 |  | 0 | 177612.8829 | 0 | 0 | FY 2022 Dec: 11 |  |  | 11 |  | 11 |  | 12
C | Support to FO and MSMEs on business proposal writting and fundraising | Access to short-term finance | # of FO and MSMEs supported | entities | 1 | 65 | 50000 | 51310.3884 | 59862.1198 | 51310.3884 | 8551.7314 |  | High |  |  | Subcomponent 2 - Access to short-term finance | Consultancies, Trainings and Services | 0.85714 | 0.14286 | 0 | 51310.3884 | 8551.7314 | 0 | 1 |  | 0 | 51310.3884 | 0 | 0
D | Co-finance fish farming inputs, post-harvest handling, feed processing facilities and equipment and others | Access to short-term finance | Business proposals financed |  | 1 | 70 | 500000 | 552573.4133 | 580202.084 | 552573.4133 |  | 27628.6707 | High |  |  | Subcomponent 2 - Access to short-term finance | Funds | 0.95238 | 0 | 0.047619 | 552573.4133 | 0 | 27628.6707 |  |  | 1 | 0 | 0 | 552573.4133 | FY 2022 Dec: 18 |  |  | 18 |  | 18 |  | 16
[8 empty] | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | 0 | 0 | 0
| TOTAL | [6 empty] | 3008036.4675 | 3306672.4344 | 3008036.4675 | 197428.1949 | 101207.772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3008036.4675 | 197428.1949 | 101207.772 | 3 | 0 | 1 | 1002526.0499 | 1001539.3117 | 1003971.1059 | FY 2022 Jan: 0; FY 2022 Feb: 0; FY 2022 Mar: 0; FY 2022 Apr: 0; FY 2022 May: 0; FY 2022 Jun: 0; FY 2022 Jul: 0
|  |  | Outreach Interventions | REFP | PROCAVA | PRODAPE | TOTAL
|  |  | Cassava input support packages (stems, agrochemicals) |  | 2000 |  | 2000
|  |  | Irish potato input support packages (seeds, agrochemicals) |  | 200 |  | 200
|  |  | Beans input support packages (seeds, agrochemicals) |  | 1500 |  | 1500 | [20 empty] | -4065.3615
|  |  | Establish Certified (C1) Cassava stems with emergent farmers & local enterpreneurs |  | 35 |  | 35
|  |  | Produce Certified (C1) Irish potato mini-tubers with emergent farmers & local enterpreneurs |  | 10 |  | 10
|  |  | Produce Certified (C1) Beans with emergent farmers & local enterpreneurs |  | 30 |  | 30
|  |  | Irrigation kits |  | 100 |  | 100
|  |  | Acquaculture inputs |  |  | 900 | 900
|  |  | Credit Line | 2500 |  |  | 0
|  |  | Cassava inputs produced by emergent farmers |  | 2200 |  | 2200
|  |  | Irish potato inputs produced by emergent farmers |  | 325 |  | 325
|  |  | Beans inputs produced by emergent farmers |  | 1700 |  | 1700
|  |  | Access to value addition facilities (Agroprocessing facilities) |  | 300 |  | 300
|  |  | Access to processing facilities |  |  | 500 | 500
|  |  | Market information |  | 9800 |  | 9800
|  |  | TOTAL | 2500 | 8400 | 1400 | 9800

## cri_costabs
description | tompro_key | subcomponentname_pt | indicators | indicator_unit | meta | ceiling | ceiling2 | cri_usd | gdm_usd | benef_usd | expenditure | fa_categories | cri_grant1 | gov2020 | benef2020 | refp_managed | procava_managed | prodape_managed | pdr_category
Establish Cassava stems multiplication plots in collaboration with IIAM (new varieties with high starch content) | 450101 | Access to affordable inputs and basic assets | # of stems, seedlings, cuttings or plantlets produced | units | 750000 | 17761.2883 | 22201.6104 | 17761.2883 | 4440.3221 |  | 1.1 - Equipment and Materials | Equipment and Materials | 0.8 | 0.2 | 0 |  | 1 | 0
Produce Foundation Irish potato mini-tubers in collaboration with IIAM | 450102 | Access to affordable inputs and basic assets | kg of seed produced | kg | 60000 | 28418.0613 | 35522.5766 | 28418.0613 | 7104.5153 |  | 1.1 - Equipment and Materials | Equipment and Materials | 0.8 | 0.2 | 0 |  | 1 | 0
Produce Foundation Beans in collaboration with IIAM | 450103 | Access to affordable inputs and basic assets | kg of seed produced | kg | 1250 | 2960.2147 | 3700.2684 | 2960.2147 | 740.0537 |  | 1.1 - Equipment and Materials | Equipment and Materials | 0.8 | 0.2 | 0 |  | 1 | 0
Establish Certified (C1) Cassava stems with emergent farmers & local enterpreneurs | 450201 | Access to affordable inputs and basic assets | # of stems, seedlings, cuttings or plantlets produced | units | 7000000 | 82886.012 | 91174.6132 | 82886.012 | 8288.6012 |  | 1.1 - Equipment and Materials | Equipment and Materials | 0.9091 | 0.0909 | 0 |  | 1 | 0
Produce Certified (C1) Irish potato mini-tubers with emergent farmers & local enterpreneurs | 450202 | Access to affordable inputs and basic assets | kg of seed produced | kg | 160000 | 63151.2472 | 75781.4967 | 63151.2472 | 12630.2494 |  | 1.1 - Equipment and Materials | Equipment and Materials | 0.8333 | 0.1667 | 0 |  | 1 | 0
Produce Certified (C1) Beans with emergent farmers & local enterpreneurs | 450203 | Access to affordable inputs and basic assets | kg of seed produced | kg | 37500 | 29602.1471 | 38482.7913 | 29602.1471 | 5920.4294 | 2960.2147 | 1.1 - Equipment and Materials | Equipment and Materials | 0.7692 | 0.1538 | 0.0769 |  | 1 | 0
Cassava input support packages (stems, agrochemicals) | 450301 | Access to affordable inputs and basic assets | # of households assessing inputs and/or technological packages | households | 2000 | 157878.1181 | 181559.8358 | 157878.1181 | 15787.8118 | 7893.9059 | 1.1 - Equipment and Materials | Equipment and Materials | 0.8696 | 0.087 | 0.0435 |  | 1 | 0
Irish potato input support packages (seeds, agrochemicals) | 450302 | Access to affordable inputs and basic assets | # of households assessing inputs and/or technological packages | households | 200 | 126302.4945 | 145247.8686 | 126302.4945 | 12630.2494 | 6315.1247 | 1.1 - Equipment and Materials | Equipment and Materials | 0.8696 | 0.087 | 0.0435 |  | 1 | 0
Beans input support packages (seeds, agrochemicals) | 450303 | Access to affordable inputs and basic assets | # of households assessing inputs and/or technological packages | households | 1500 | 142090.3063 | 163403.8522 | 142090.3063 | 14209.0306 | 7104.5153 | 1.1 - Equipment and Materials | Equipment and Materials | 0.8696 | 0.087 | 0.0435 |  | 1 | 0
Establish trials on inclusion of cassava flour on backing industry | 450401 | Access to affordable inputs and basic assets | # of reports prepared and approved | reports | 1 | 34733.186 | 34733.186 | 34733.186 |  |  | 1.1 - Equipment and Materials | Equipment and Materials | 1 | 0 | 0 |  | 1 | 0
Establish and pilot a market information system for value chain stakeholders | 450402 | Access to affordable inputs and basic assets | # of management information sistems - MIS, established and operational | systems | 1 | 39469.5295 | 39469.5295 | 39469.5295 |  |  | 1.1 - Equipment and Materials | Equipment and Materials | 1 | 0 | 0 |  | 1 | 0
Establish pilots on use of renewable energy for value-addition facilities (solar powered processing kits) | 450403 | Access to affordable inputs and basic assets | # of units | units | 5 | 94726.8709 | 104199.5579 | 94726.8709 | 4736.3435 | 4736.3435 | 1.1 - Equipment and Materials | Equipment and Materials | 0.9091 | 0.0455 | 0.0455 |  | 1 | 0
Promote low-cost & energy saving small-scale irrigation systems (solar powered drip kits) | 450404 | Access to affordable inputs and basic assets | # of units | units | 5 | 181559.8358 | 199715.8194 | 181559.8358 | 9077.9918 | 9077.9918 | 1.1 - Equipment and Materials | Equipment and Materials | 0.9091 | 0.0455 | 0.0455 |  | 1 | 0
Installation of floating fish cages in Nampula | 450501 | Access to affordable inputs and basic assets | # of floating cages installed | units | 50 | 142090.3063 | 163403.8522 | 142090.3063 | 14209.0306 | 7104.5153 | 3.1 - Technical Assistance | Consultancies, Trainings and Services | 0.8696 | 0.087 | 0.0435 |  |  | 1
Finalize feed processing facility in Lichinga | 450502 | Access to affordable inputs and basic assets | Processing facilities constructed/rehabilitated | facilities | 1 | 40701.9656 | 48842.3587 | 40701.9656 | 4070.1966 | 4070.1966 | 3.1 - Technical Assistance | Consultancies, Trainings and Services | 0.8333 | 0.0833 | 0.0833 |  |  | 1
Rehabilitation and expansion of climate resilient fish ponds in Milange and Ribáue | 450503 | Access to affordable inputs and basic assets | Fishponds constructed/rehabilitated | ponds | 60 | 80151.563 | 104197.0319 | 80151.563 | 8015.1563 | 16030.3126 | 3.1 - Technical Assistance | Consultancies, Trainings and Services | 0.7692 | 0.0769 | 0.1538 |  |  | 1
Supply of acquaculture inputs in Zambézia, Niassa and Nampula | 450601 | Access to affordable inputs and basic assets | # of households assessing inputs and/or technological packages | households | 900 | 149344.9045 | 164279.3949 | 149344.9045 | 7467.2452 | 7467.2452 | 1.1 - Equipment and Materials | Equipment and Materials | 0.9091 | 0.0455 | 0.0455 |  |  | 1
Alocate feed processing kits to smallholder fish farmers | 450602 | Access to affordable inputs and basic assets | Processing facilities constructed/rehabilitated | facilities | 2 | 720.1117 | 792.1229 | 720.1117 | 36.0056 | 36.0056 | 1.1 - Equipment and Materials | Equipment and Materials | 0.9091 | 0.0455 | 0.0455 |  |  | 1
Train extension officers on fish production | 450701 | Access to affordable inputs and basic assets | # of public and private entities staff trained | staff | 30 | 18977.1349 | 24561.9937 | 18977.1349 | 5584.8588 |  | 3.5 - Trainings | Operating Costs | 0.7726 | 0.2274 | 0 |  |  | 1
Train fish farmers on fish production | 450702 | Access to affordable inputs and basic assets | # of producers trained on sustainable production practices | producers | 90 | 3757.1045 | 9341.9633 | 3757.1045 | 5584.8588 |  | 3.5 - Trainings | Operating Costs | 0.4022 | 0.5978 | 0 |  |  | 1
Allocate fish handling and conservation kits (isothermal crates, scales, nives and others) | 450801 | Access to affordable inputs and basic assets | People receiving enterpreneurship kits | producers | 50 | 15654.6021 | 17220.0624 | 15654.6021 | 782.7301 | 782.7301 | 1.1 - Equipment and Materials | Equipment and Materials | 0.9091 | 0.0455 | 0.0455 |  |  | 1
Establish a line of credit for operating costs (inputs for outgrower schemes and FO) | 460901 | Access to short-term finance | # of FO and MSMEs supported | entities | 100 | 773602.7787 | 812282.9176 | 773602.7787 | 38680.1389 |  | 4.1 - Funds | Funds | 0.9524 | 0.0476 | 0 | 1 |  | 0
Establish a line of credit for small-scale investments (farm mechanization, value-addition, transportation & marketing) | 460902 | Access to short-term finance | # of FO and MSMEs supported | entities | 45 | 177612.8829 | 186493.527 | 177612.8829 | 8880.6441 |  | 4.1 - Funds | Funds | 0.9524 | 0.0476 | 0 | 1 |  | 0
Support to FO and MSMEs on business proposal writting and fundraising | 461001 | Access to short-term finance | # of FO and MSMEs supported | entities | 65 | 51310.3884 | 59862.1198 | 51310.3884 | 8551.7314 |  | 3.1 - Technical Assistance | Consultancies, Trainings and Services | 0.8571 | 0.1429 | 0 | 1 |  | 0
Co-finance fish farming inputs, post-harvest handling, feed processing facilities and equipment and others | 460903 | Access to short-term finance | Business proposals financed | lumpsum | 70 | 552573.4133 | 580202.084 | 552573.4133 |  | 27628.6707 | 4.1 - Funds | Funds | 0.9524 | 0 | 0.0476 |  |  | 1

## RESUMO
Table 1 - Programme Budget by Component and Financier (US$)
Subcomponents | IFAD CRI Financing (US$) | GoM in-kind (US$) | Beneficiaries in-kind (US$) | TOTAL COST (US$)
Access to affordable inputs and basic assets | 1452937 | 141315.68 | 73579.1 | 1667831.79
Access to short-term finance | 1555099.46 | 56112.51 | 27628.67 | 1638840.65
Grand Total | 3008036.47 | 197428.19 | 101207.77 | 3306672.43
Table 2 - Programme Budget by Category and Financier (US$) – External Resources
Subcomponents | IFAD CRI Financing (US$) | GoM in-kind (US$) | Beneficiaries in-kind (US$) | TOTAL COST (US$)
Consultancies, Trainings and Services | 314254.22 | 34846.11 | 27205.02 | 314254.22
Equipment and Materials | 1167258.93 | 103851.58 | 46374.08 | 1167258.93
Funds | 1503789.07 | 47560.78 | 27628.67 | 1503789.07
Operating Costs | 22734.24 | 11169.72 |  | 22734.24
Grand Total | 3008036.47 | 197428.19 | 101207.77 | 3008036.47
Table 3 - Programme Budget by Implementing Agency (Project / Programme) and Financing Category (US$) – External Resources
Subcomponents | Managed by REFP (US$) | Managed by PROCAVA(US$) | Managed by PRODAPE(US$) | TOTAL COST (US$)
Consultancies, Trainings and Services | 51310.39 | - | 262943.83 | 314254.22
Equipment and Materials | - | 1001539.31 | 165719.62 | 1167258.93
Funds | 951215.66 | - | 552573.41 | 1503789.07
Operating Costs | - | - | 22734.24 | 22734.24
Grand Total | 1002526.05 | 1001539.31 | 1003971.11 | 3008036.47

## Sheet7
Componentes | Acções | Meta | Indicador | Estimativa de beneficiários directos |  |  | Informações adicionais | Tipo de despesa | Custo Unitário (MT) | Custo Total (MT) | Custo Total (US$)
|  |  |  | Total | Homens | Mulheres
Subcomponent 1 - Access to affordable inputs and basic assets |  |  |  | 20 | 10 | 10 | 20 gaiolas flutuantes em Niassa produção esperada de 43 toneladas por ciclo |  | 200000 | 4000000 | 62500
Subcomponent 1 - Access to affordable inputs and basic assets |  |  |  | 1 | 1 | 0 |  |  | 260000 | 2600000 | 40625
Subcomponent 1 - Access to affordable inputs and basic assets |  |  |  | 60 | 30 | 30 | 80 tanques - produção esperada de 84 toneladas por ciclo |  | 80000 | 4800000 | 75000
Subcomponent 1 - Access to affordable inputs and basic assets |  |  |  | 90 | 30 | 60 | 300.000 alevinos (100 para gaiolas e 200 para tanques) |  | 8 | 1440000 | 22500
Subcomponent 1 - Access to affordable inputs and basic assets |  |  |  | 90 | 30 | 60 | 100.000 kg de racao |  | 90 | 8100000 | 126562.5
Subcomponent 1 - Access to affordable inputs and basic assets |  |  |  | 90 | 30 | 60 | Maquinetas para moer, misturar ingreidentes e peletizar |  | 23000 | 46000 | 718.75
Subcomponent 1 - Access to affordable inputs and basic assets |  |  |  | 30 | 15 | 15 |  |  | 404080 | 1212240 | 18941.25
Subcomponent 1 - Access to affordable inputs and basic assets |  |  |  | 90 | 30 | 60 | Treinamento dos aquacultores em matérias de (i) abertura de tanques (ii) construção de gaiolas (iii) gestão do cultivo (iv) produção de dietas melhoradas (v) técnicas de colheita (VI) boas praticas (VII) dissiminacao de tecnicas melhoradas |  | 80000 | 240000 | 3750
Subcomponent 1 - Access to affordable inputs and basic assets |  |  |  | 60 | 30 | 30 |  |  | 20000 | 400000 | 6250
Subcomponent 3 - Access to Market Information |  |  |  | 90 | 30 | 60 | Recolha de informação estatística de base nos locais de produção, de venda de pescado |  | 18610 | 818840 | 12794.375
Subcomponent 3 - Access to Market Information |  |  |  | 90 | 30 | 60 | Instalados sistemas de recolha de dados nas Delegações provinciais do IDEPA |  | 830570 | 5813990 | 90843.5938
Subcomponent 3 - Access to Market Information |  |  |  | 90 | 30 | 60 | As informações serão divulgadas em todos os distritos do PRODAPE, sendo uma por mês |  | 9340 | 2577840 | 40278.75
Subcomponent 3 - Access to Market Information |  |  |  | 500 | 200 | 300 | Promocao de produtos, insumos e servicos da aquacultura |  | 130070 | 390210 | 6097.0312
Subcomponent 2 - Access to short-term finance |  |  |  | 23 | 10 | 13 | Fabriqueta de producao de gelo, camara de conservacao de pescado, arcas frigorificas, caixas isotérmicas |  | 70040 | 1610920 | 25170.625
Subcomponent 2 - Access to short-term finance |  |  |  | 59 | 29 | 30 | Gaiolas, tanques, ração, alevinos, maquinetas de racao e outros equipamentos |  | 115100 | 6790900 | 106107.8125
Subcomponent 2 - Access to short-term finance |  |  |  | 15 | 8 | 7 | Projecto de negocios, incluindo iniciativas de empereendedorismo para jovens |  | 200000 | 3000000 | 46875
Subcomponent 2 - Access to short-term finance |  |  |  | 1 | 1 | 0 |  |  | 4800000 | 4800000 | 75000
Subcomponent 2 - Access to short-term finance |  |  |  | 3 | 2 | 1 |  |  | 2540000 | 7620000 | 119062.5
Subcomponent 2 - Access to short-term finance |  |  |  | 15 | 8 | 7 |  |  | 200000 | 3000000 | 46875
Subcomponent 2 - Access to short-term finance |  |  |  | 60 | 30 | 30 |  |  | 80000 | 4800000 | 75000
ID | Activity | Old indicator | Indicator | Units | Freq. | Quantity | Unit Price (MZN) | Cost | Priority | Geographical Distribution, ex. Mapai (22), Mabalane (16) | Comments | Component | Category | CRI (%) | Government (%) | Beneficiaries (%) | CRI (MZN) | Government (MZN) | Beneficiaries (MZN) | REFP (%) | PROCAVA (%) | PRODAPE (%)
1 | Implantação de unidades de gaiolas flutuantes em Niassa e Nampula |  | No de gaiolas implantadas |  | 1 | 20 |  | 62500 | High |  |  |  | Servicos
2 | Expansao/Conclusao de Unidade de Producao de Racao em Lichinga |  | Nr de unidade expandida/concluida |  | 1 | 1 |  | 40625 | High |  |  |  | Servicos & Bens
3 | Reabilitacao e Expansao tanques aquicolas resilientes as mudanças climáticas em Milange e Ribuae |  | No de tanques implantados/reabilitados |  | 1 | 60 |  | 75000 | High |  |  |  | Servicos & Bens
4 | Fornecimento de insumos aquicolas - Alevinos para Zambezia, Niassa e Nampula |  | No de alevinos adquiridos |  | 1 | 180000 |  | 22500 | High |  |  |  | Bens
5 | Fornecimento de insumos aquicolas - Ração para Zambezia, Niassa e Nampula |  | Kilogramas de ração adquirida |  | 1 | 90000 |  | 126562.5 | High |  |  |  | Bens
6 | Aquisicao de maquinetas de producao de racao para Zambezia e Nampula |  | No de maquinetas adquiridas |  | 1 | 2 |  | 718.75 | High |  |  |  | Bens
7 | Treinamento de extensionistas em técnicas de cultivo de peixe em tanques e gaiolas em Niassa, Zambezia e Nampula |  | No de sessoes realizadas |  | 1 | 3 |  | 18941.25 | High |  |  |  | Custos Operacionais
8 | Treinamento de aquacultores em técnicas de cultivo de peixe em tanques e gaiolasm Niassa, Zambezia e Nampula |  | No de sessoes realizadas |  | 1 | 3 |  | 3750 | High |  |  |  | Custos Operacionais
9 | Aquicisao de kits de manuseamento e conseravacao do pescado [caixas isotermicas, balanca, facas e tabuas de evisceracao] |  | No de kits adquiridos |  | 1 | 20 |  | 6250 | High
10 | Aquisição dispositivos elecrtonicos para operacionalização do sistema de recolha de preços |  | No de dispositivos electronicos adquiridos |  | 1 | 44 |  | 12794.375 | High |  |  |  | Custos operacionais
11 | Instalação do sistema de recolha de informação de sobre mercados de pesca e aquacultura |  | No de sistemas instalados |  | 1 | 7 |  | 90843.5938 | High |  |  |  | Custos operacionais
12 | Recolha e divulgação de preços de insumos e pescado |  | No de divulgações na rádio |  | 1 | 276 |  | 40278.75 | High |  |  |  | Custos operacionais
13 | Realizacao de feiras locais de pescado em Niassa, Nampula e Zambezia |  | No de feiras realizadas |  | 1 | 3 |  | 6097.0312 | High |  |  |  | Custos operacionais
14 | Financiar a aquisicao de equipamento de frio, material de manuseamento e conservacao de pescado [ fabriqueta de gelo, congeladores, caixas isotermicas ] |  | Nr de individuos financiados |  | 1 | 23 |  | 25170.625 | High |  |  |  | Servicos
15 | Financiar a aquisicao de insumos de producao |  | Nr de individuos financiados |  | 1 | 59 |  | 106107.8125 | High |  |  |  | Servicos
16 | Financiamento a iniciativa de negócios na cadeia de valor da aquacultura. |  | Nr de individuos financiados |  | 1 | 15 |  | 46875 | High |  |  |  | Servicos
17 | Finnciamento de expansao de unidades de producao de racao de nivel comercial |  | Nr de unidades de racao financiadas |  | 1 | 1 |  | 75000 | High
18 | Financiamento de expansao unidades de producao de alevinos |  | Nr de unidades de alevenios fianciados |  | 1 | 3 |  | 119062.5 | High
19 | Financiamento de expansao de unidades de producao de gaiolas |  | Nr de gaiolas financiados |  | 1 | 15 |  | 46875 | High
20 | Financiamento de expansao de unidades de producao de tanques |  | Nr de tanques financiados |  | 1 | 60 |  | 75000 | High

## Sheet4
Row Labels | Count of District
Cassava | 7
Chicken | 13
Irish Potato | 13
Onion | 9
Sweet potato | 22
Grand Total | 64

## Sheet3
Commodity | District | PROCAVA | Beneficiaries | Moamba | Moamba, Matutuíne, Boane, Namaacha, Massinga, Vilankulo, Chókwè, Guijá, Chibuto, Sanga, Muembe, Ngauma, Chimbunila, Bilene, Mapai, Mandlakazi, Mabalane, Govuro, Mabote, Funhalouro, Zavala, Jangamo, Cuamba, Mecanhelas, Inharrime, Morrumbene, Homoíne
Irish Potato | Moamba |  |  | Matutuíne
Irish Potato | Matutuíne |  |  | Boane
Irish Potato | Boane |  |  | Namaacha
Irish Potato | Namaacha |  |  | Massinga
Irish Potato | Massinga |  |  | Vilankulo
Irish Potato | Vilankulo |  |  | Chókwè
Irish Potato | Chókwè |  |  | Guijá
Irish Potato | Guijá |  |  | Chibuto
Irish Potato | Chibuto |  |  | Sanga
Irish Potato | Sanga |  |  | Muembe
Irish Potato | Muembe |  |  | Ngauma
Irish Potato | Ngauma |  |  | Chimbunila
Irish Potato | Chimbunila |  |  | Bilene
Chicken | Bilene |  |  | Mapai
Chicken | Mapai |  |  | Mandlakazi
Chicken | Mandlakazi |  |  | Mabalane
Chicken | Mabalane |  |  | Govuro
Chicken | Govuro |  |  | Mabote
Chicken | Mabote |  |  | Funhalouro
Chicken | Funhalouro |  |  | Zavala
Chicken | Massinga |  |  | Jangamo
Chicken | Zavala |  |  | Cuamba
Chicken | Jangamo |  |  | Mecanhelas
Chicken | Cuamba |  |  | Inharrime
Chicken | Mecanhelas |  |  | Morrumbene
Chicken | Ngauma |  |  | Homoíne
Cassava | Mandlakazi
Cassava | Zavala
Cassava | Inharrime
Cassava | Jangamo
Cassava | Morrumbene
Cassava | Massinga
Cassava | Homoíne
Onion | Moamba
Onion | Boane
Onion | Namaacha
Onion | Guijá
Onion | Chókwè
Onion | Massinga
Onion | Chimbunila
Onion | Muembe
Onion | Sanga
Sweet potato | Matutuíne
Sweet potato | Boane
Sweet potato | Massinga
Sweet potato | Vilankulo
Sweet potato | Chókwè
Sweet potato | Guijá
Sweet potato | Chibuto
Sweet potato | Sanga
Sweet potato | Muembe
Sweet potato | Ngauma
Sweet potato | Chimbunila
Sweet potato | Bilene
Sweet potato | Mapai
Sweet potato | Mandlakazi
Sweet potato | Mabalane
Sweet potato | Govuro
Sweet potato | Mabote
Sweet potato | Zavala
Sweet potato | Jangamo
Sweet potato | Inharrime
Sweet potato | Morrumbene
Sweet potato | Homoíne

## Sheet2
indicator_en | indicator_units
# of 50 kg hermetic bags allocated | bags
# of 500 hermetic silo bags allocated | silos
# of action plans prepared, approved and implemented | plans
# of administrative infrastructure constructed, rehabilitated, constructed and/or equiped | infrastructures
# of agricultural training centres constructed, rehabilitated and/or improved | centres
# of agrometeorological system established and operational | system
# of agroprocessing kits allocated | kits
# of air tickets issued | tickets
# of animals of improved breeds allocated | animals
# of animals of local breeds allocated | animals
# of annual impact evaluation studies conducted | studies
# of business proposals supported | proposals
# of certified products promoted by PROCAVA | products
# of community grazing areas delimitated and with land certificate issued | delimitations
# of community radios contracted | radios
# of community vaccinators trainned and/or equiped | vaccinators
# of contracts closed | contracts
# of contracts secured | contracts
# of crops demonstration, research or learning plots or units established | units
# of crops processing infrastructure constructed, rehabilitated or equiped | infrastructures
# of districts targeted | districts
# of DUATs registered in the National Cadastre | DUATs
# of electronic data collection and retrieval devices allocated | devices
# of employees targeted | technicians
# of employments created by PROCAVA related interventions | employments
# of financial management sistems - FMS, established and operational | systems
# of FO and MSMEs supported | entities
# of households assessing inputs and/or technological packages | households
# of households assisted in crop production practices | households
# of households assisted in livestock production practices | households
# of households targeted by land resources planning | households
# of households trained in nutrition and agro-processing | households
# of improved silos constructed or allocated | silos
# of infraestructure management personel trained | people
# of infrastructure and equipment management committees strengthened | comités
# of infrastructure constructed, rehabilitated and/or equiped | infrastructures
# of infrastructure with technical studies and/or designs delivered | infrastructures
# of infrastructure with tenders launched | infrastructures
# of inter-institutional agreements signed | aggreements
# of irrigation kits supplied and installed | kits
# of irrigation management personel capacitated | people
# of kits allocated and/or installed | kits
# of knowledge management events, meetings or workshops organized | policy tools
# of knowledge transfer tools developed | tools
# of learning groups established and trained | groups
# of livestock demonstration, research or learning plots or units established | units
# of livestock management infrastructure constructed, rehabilitated and/or improved | infrastructures
# of livestock processing infrastructure constructed, rehabilitated or equiped | infrastructures
# of local agriculture service providers equiped | service providers
# of local agriculture service providers trained | service providers
# of local livestock service providers (AHAs) equiped | service providers
# of local livestock service providers (AHAs) trained | service providers
# of localities targeted by PROCAVA | localities
# of management information sistems - MIS, established and operational | systems
# of marketing events/fairs promoted | events
# of marketing infrastructure constructed, rehabilitated or equiped | infrastructures
# of marketing kits allocated | proposals
# of mechanization kits allocated | kits
# of men × days employed | men × days
# of men × months employed | men × months
# of missions, monitoring and/or data validation visits carried out | missions or visits
# of months covered (operating expenses) | months
# of motorbyke × months covered | motorbyke × months
# of motorbykes procured and allocated | motorbykes
# of multipurpose water infrastructure constructed, rehabilitated or improved | infrastructures
# of multi-stakeholder platforms established and operational | platforms
# of national brands/products supported and/or introduced to the markets | brands
# of new and improved varieties released | varieties
# of nutrition and/or sanitation kits allocated | nutrition/sanitation kits
# of nutrition promoters trained | promoters
# of packaging materials designed, reproduced and allocated | packages
# of packaging materials' samples reproduced | packages
# of pages reviewed and/or translated | pages
# of PMUs established and operational | PMUs
# of policy relevant knowledge products completed | policy tools
# of producers and value chain actors trained in agribusiness aspects | producers and/or actors
# of programme management units established and/or operational | units
# of public and private entity staff equiped | kits
# of public and private entity staff trained | technicians
# of rain gauges procured and installed | gauges
# of reports prepared and approved | reports
# of research infrastructure operational | infrastructure
# of rural infrastructure with environmental compliance secured | infrastructures
# of rural producers receiving project services (recorded and coded) | producers
# of seed producers trained | seed producers
# of service-days delivered | days
# of smallholder farmers benefiting from agricultural inputs and/or technological packages | producers
# of smallholder farmers benefiting from livestock inputs and/or technological packages | producers
# of smallholder farmers trained on sustainable production practices | producers
# of stems, seedlings, cuttings or plantlets produced | units
# of storage infrastructure constructed, rehabilitated or equiped | infrastructures
# of studies, surveys and/or reports delivered | studies
# of technological packages, training materials and/or guidelines developed | packages
# of trees planted | trees
# of units | units
# of value chains actors reached by MIS | actors
# of vehicle × months covered | vehicle × months
# of vehicles procured and allocated | vehicles
# of water related infrastructure with environmental compliance secured | infrastructures
baseline study conducted | studies
gender strategy completed and approved | strategies
hectares of farmland demarcated and registered into national cadastre | hectares
hectares of farmland under irrigation | hectares
hectares of farmland under irrigation with technical designs completed | hectares
hectares of grazing land established | hectares
household farm income in USD per household | USD
kg of seed produced | kg
km of transmission lines installed | km
mid-term evaluation conducted | studies
minutes of radiotransmission | minutes
months of internships hosted | interns